## Example
Capacity, Commited, Effort, and Delivered Metric
Sprint: | 1
Team: | Team Fun
Scrum Master: | Eric Pogue
Product Owner | James Pogue
Name | Estimated Capacity (hours) | Story Points Committed | Hours Worked/Effort (hours) | Story Points Delivered | Capacity to Effort (%) | Committed to Delivered (%) | Capacity to Delivered (%)
Eric Pogue | 12 | 11 | 10 | 8 | 83.33% | 72.73% | 66.67%
James Pogue | 12 | 14 | 14 | 12 | 116.7% | 85.71% | 100%
Ted Danson | 12 | 6 | 4 | 3 | 33.33% | 50% | 25%
Team Totals: | 36 | 31 | 28 | 23 | 77.78% | 74.19% | 63.89%
Preliminary Signoff | Initial |  | Date/Time
Product Owner | JP |  | January 29, 2023 @ 11:58 pm
Scrum Master | EJP |  | January 29, 2023 @ 11:59 pm
Final Signoff | Initial |  | Date
Product Owner | JP |  | January 30, 2023 @ 2:06 pm
Scrum Master | EJP |  | January 30, 2023 @ 2:07 pm

## Sprint4
Capacity, Commited, Effort, and Delivered Metric
Sprint: | 4
Team: | BearDown
Scrum Master: | Erick Hernandez
Product Owner | Sebastian Jaculbe
Name | Estimated Capacity (hours) | Story Points Committed | Hours Worked/Effort (hours) | Story Points Delivered | Capacity to Effort (%) | Committed to Delivered (%) | Capacity to Delivered (%)
Sebastian Jaculbe | 6 | 16 | 6 | 16 | 100% | 100% | 266.7%
Kevin Brian Dacanay | 6 | 17 | 6 | 17 | 100% | 100% | 283.3%
Erick Hernandez | 6 | 14 | 6 | 14 | 100% | 100% | 233.3%
Kaleb Richardson | 6 | 14 | 6 | 14 | 100% | 100% | 233.3%
Edward Rodriguez | 6 | 12 | 6 | 12 | 100% | 100% | 200%
Team Member 6 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Team Totals: | 30 | 73 | 30 | 73 | 100% | 100% | 243.3%
Preliminary Signoff | Initial |  | Date/Time
Product Owner | SDJ |  | April 7, 2026 @ 9:38 pm
Scrum Master |  |  | January 29, 2023 @ 11:59 pm
Final Signoff | Initial |  | Date
Product Owner | SDJ |  | January 30, 2023 @ 2:06 pm
Scrum Master |  |  | January 30, 2023 @ 2:07 pm

## Sprint5
Capacity, Commited, Effort, and Delivered Metric
Sprint: | 5
Team: | BearDown
Scrum Master: | Erick Hernandez
Product Owner | Sebastian Jaculbe
Name | Estimated Capacity (hours) | Story Points Committed | Hours Worked/Effort (hours) | Story Points Delivered | Capacity to Effort (%) | Committed to Delivered (%) | Capacity to Delivered (%)
Sebastian Jaculbe | 6 | 22 | 6 | 22 | 100% | 100% | 366.7%
Kevin Brian Dacanay | 6 | 25 | 6 | 25 | 100% | 100% | 416.7%
Erick Hernandez | 6 | 25 | 6 | 25 | 100% | 100% | 416.7%
Kaleb Richardson | 6 | 15 | 6 | 15 | 100% | 100% | 250%
Edward Rodriguez | 6 | 13 | 6 | 13 | 100% | 100% | 216.7%
Team Member 6 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Team Totals: | 30 | 100 | 30 | 100 | 100% | 100% | 333.3%
Preliminary Signoff | Initial |  | Date/Time
Product Owner | SDJ |  | April 13, 2026 @ 12:04 am
Scrum Master |  |  | January 29, 2023 @ 11:59 pm
Final Signoff | Initial |  | Date
Product Owner | SDJ |  | April 13, 2026 @ 12:04 am
Scrum Master |  |  | January 30, 2023 @ 2:07 pm

## Sprint6
Capacity, Commited, Effort, and Delivered Metric
Sprint: | 6
Team: | BearDown
Scrum Master: | Eric Pogue
Product Owner | James Pogue
Name | Estimated Capacity (hours) | Story Points Committed | Hours Worked/Effort (hours) | Story Points Delivered | Capacity to Effort (%) | Committed to Delivered (%) | Capacity to Delivered (%)
Sebastian Jaculbe | 8 | 1 | 1 | 1 | 12.5% | 100% | 12.5%
Kevin Brian Dacanay | 8 | 1 | 1 | 1 | 12.5% | 100% | 12.5%
Erick Hernandez | 8 | 1 | 1 | 1 | 12.5% | 100% | 12.5%
Kaleb Richardson | 8 | 1 | 1 | 1 | 12.5% | 100% | 12.5%
Edward Rodriguez | 8 | 1 | 1 | 1 | 12.5% | 100% | 12.5%
Team Member 6 | 0 | 1 | 1 | 1 | #DIV/0! | 100% | #DIV/0!
Team Totals: | 40 | 6 | 6 | 6 | 15% | 100% | 15%
Preliminary Signoff | Initial |  | Date/Time
Product Owner | ER |  | April 16, 2026 @ 9:47 am
Scrum Master |  |  | January 29, 2023 @ 11:59 pm
Final Signoff | Initial |  | Date
Product Owner | JP |  | January 30, 2023 @ 2:06 pm
Scrum Master | EJP |  | January 30, 2023 @ 2:07 pm

## Sprint7
Capacity, Commited, Effort, and Delivered Metric
Sprint: | 7
Team: | BearDown
Scrum Master: | Eric Pogue
Product Owner | James Pogue
Name | Estimated Capacity (hours) | Story Points Committed | Hours Worked/Effort (hours) | Story Points Delivered | Capacity to Effort (%) | Committed to Delivered (%) | Capacity to Delivered (%)
Sebastian Jaculbe | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Kevin Brian Dacanay | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Erick Hernandez | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Kaleb Richardson | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Edward Rodriguez | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Member 6 | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Totals: | 6 | 6 | 6 | 6 | 100% | 100% | 100%
Preliminary Signoff | Initial |  | Date/Time
Product Owner | JP |  | January 29, 2023 @ 11:58 pm
Scrum Master | EJP |  | January 29, 2023 @ 11:59 pm
Final Signoff | Initial |  | Date
Product Owner | JP |  | January 30, 2023 @ 2:06 pm
Scrum Master | EJP |  | January 30, 2023 @ 2:07 pm

## Sprint8
Capacity, Commited, Effort, and Delivered Metric
Sprint: | 8
Team: | BearDown
Scrum Master: | Eric Pogue
Product Owner | James Pogue
Name | Estimated Capacity (hours) | Story Points Committed | Hours Worked/Effort (hours) | Story Points Delivered | Capacity to Effort (%) | Committed to Delivered (%) | Capacity to Delivered (%)
Sebastian Jaculbe | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Kevin Brian Dacanay | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Erick Hernandez | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Kaleb Richardson | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Edward Rodriguez | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Member 6 | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Totals: | 6 | 6 | 6 | 6 | 100% | 100% | 100%
Preliminary Signoff | Initial |  | Date/Time
Product Owner | JP |  | January 29, 2023 @ 11:58 pm
Scrum Master | EJP |  | January 29, 2023 @ 11:59 pm
Final Signoff | Initial |  | Date
Product Owner | JP |  | January 30, 2023 @ 2:06 pm
Scrum Master | EJP |  | January 30, 2023 @ 2:07 pm